## Sheet1
User Stories
| Snow | Matt | David | Juno
As a designer, I want to create five game levels. | 3 | 3 | 3 | 5
As a designer, I want to make and implement the remaining mini-games and levels. | 5 | 5 | 5 | 5
As a programmer, I want to implement a background using parallax scrolling. | 3 | 1 | 3 | 3
As an artist, I want to include multiple animations. | 1 | 3 | 3 | 3
As a programmer, I want to include saving and loading the game. | 3 | 3 | 5 | 3
As a team, we want to fix our editors to meet the base requirements. | 1 | 1 | 1 | 1
As a programmer, I want to add a Loading (Changing) Level State. | 3 | 3 | 1 | 1
As a programmer, I want to create a particle editor that meets base requirements. | 10 | 10 | 5 | 3
As a programmer, I want to create and implement a particle engine that meets base requirements. | 10 | 10 | 5 | 3
As a programmer, I want to implement wall jumping and any other necessary character movements. | 3 | 3 | 1 | 5
As a programmer, I want to make fixes or changes to the Tile Collision system. | 10 | 10 | 5 | 5
As a programmer, I want to make fixes or changes to the camera. | 5 | 5 | 1 | 3
As a programmer, I want to improve spawn points and use scripting for them. | 10 | 5 | 3 | 10
As a team member, I want to fill out the Credits State. | 3 | 1 | 1 | 1
As a programmer, I want to implement the out-of-game hacking concept. | 10 | 5 | 10 | 10
As a programmer, I want to improve enemy movement and AI. | 3 | 5 | 5 | 3
As a programmer, I want to create Bosses and other End-of-level Events. | 5 | 5 | 3 | 5
As a programmer, I want to implement key-binding into the options menu. | 3 | 5 | 5 | 1
As a team member, I want to modify the HUD to include a timer for hacking time limit and benefit timers. | 1 | 1 | 1 | 1
As a team member, I will speak with the artist and implement the assets into the game. | 1 | 1 | 1 | 1